## Sheet1
TASK | DESCRIPTION | VIEWS
projects tab | projects, statistics links | view statistics |  | Lora
teams tab | teams list /team name, users, active projects/task (overdue), edit team (add, remove users)/ | view profile -> view edit team |  | Evgeni/Lora
customers tab | customers list /name, details, projects - active, closed, edit | view profile -> view edit customer (modal?) |  | Evegni/Lora
users tab | users list + details, edit | view profile -> view edit user manage rates |  | Lora
project list view | filter projects by user |  |  | MJ
add description to project model and project creation view |  |  |  | MJ | Done
project profile | separate user and admin views | task edit view | change comments type / user+text | MJ | Done
add photo property of user |  |  |  | MJ | Done
Enter actual expenses |  | view expenses |  | MJ | Done
Add tab for all projects in project list |  |  |  | Lora
Add profession at user registration |  | register view |  | Lora | Done
set breadcrumb links |  |  |  | MJ
Statistics regarding user participation in project/task (No of commits/hour worked) |  |  |  | MJ
task details view/ format media body |  |  |  | Lora | Done
teams view | probably teams view should be inclused in users list view?? |  |  | Lora
user authentication | ordinary users cannot acces edit views |  |  | Evgeni | Done
search in customer list view